CPFR-in-CPH Integration Roadmap

CPFR Data Platform → Chewy Partner Hub Module

Milestone-Driven Roadmap — Draft for Review

Business Product Owner: Nathan Miles

VC Partner: Nathan Nelson

Executive Sponsor: Dave Livesay, Sr. Director, Inventory Management

Date: March 11, 2026

Status: Draft v0.1 — For Internal Review

# 1. Executive Context

Chewy’s CPFR program distributes weekly inventory and forecast data to 3,200+ vendors, serving as foundational infrastructure for the majority of ISM vendor-facing work. This roadmap charts the path from a nearly complete data platform investment to vendor-accessible capability within Chewy Partner Hub (CPH).

## 1.1 Where We Stand

The hardest investment has been made. The CPFR data platform—a Snowflake-based semantic layer with vendor isolation, daily refresh, immutable snapshots, and data lineage—is on track for 3/31/2026 delivery at network grain. This covers 98.4% of vendors (Tiers 2 & 3). Only 45 Tier 1 vendors require the SKU/FC-level granularity that constitutes a known follow-on deliverable.

What’s missing is the on-ramp. Without the CPH module, the platform investment sits idle—vendors continue receiving weekly emails assembled through manual processes that carry scaling, data integrity, and data leakage risks. The marginal cost to realize the platform’s value through a CPH module is bounded and clear, making this a completion initiative rather than a new speculative investment.

## 1.2 Funding & Resource Reality

The initiative did not secure OP1 2026 funding due to competing priorities and late insertion into the planning cycle—not a rejection of the business case on merit. It currently operates on allocation (best-effort labor, no committed headcount). A cascading series of departures has dissolved every prior connective-tissue role, leaving no assigned TPM and no confirmed CPH engineering contact for CPFR integration.

This roadmap is designed to serve two purposes: (1) coordinate what can be accomplished on allocation today, and (2) build the evidence base and momentum for an OP1 2027 funding submission that converts this from best-effort to committed.

## 1.3 Strategic Value Summary

| Value Driver | Magnitude |
| --- | --- |
| CPFR-Specific Annual Value | $1.4M projected recurring cost avoidance (ISM capacity, governance, data prep elimination) |
| VC/Chargeback Entitlement | $21M entitlement opportunity; $10.8M annual chargeback data; 1,500 Oracle CRM tickets/year reduction |
| Risk Exposure (Current State) | $5M documented single-event cost avoidance; ~$15M estimated annual exposure from recurring threshold issues; active data leakage vulnerability in manual distribution |
| Competitive Parity | Amazon (Vendor Central) and Walmart already provide equivalent portal-based vendor data access |
| Vendor Sentiment | 96% unweighted approval rating (sample-based); major vendors (Blue Buffalo, Mars, Nestlé Purina) have explicitly requested portal/API access |

# 2. Roadmap Architecture

The roadmap is organized into four phases that map to real delivery gates and leadership decision points—not arbitrary calendar quarters. Each phase has explicit entry criteria, deliverables, and the dependency gates that must clear before proceeding.

## Phase 0: Foundation & Readiness (March–May 2026)

Funding model: Allocation (current state).

Objective: Validate delivery readiness, establish coordination mechanisms, and produce the artifacts that enable all subsequent phases.

| Milestone | Target Date | Owner |
| --- | --- | --- |
| M0.1: CPFR data platform delivered (network grain) | 3/31/2026 | Stefan / SC-BIE |
| M0.2: PRFAQ finalized and circulated | 3/14/2026 | Nathan Miles |
| M0.3: CPH technical contact identified and engaged | 3/21/2026 | Nathan Miles / Erdem’s team |
| M0.4: RACI map circulated; role gaps surfaced | 3/28/2026 | Nathan Miles |
| M0.5: Technical coaching relationship activated with Erdem’s org | 4/4/2026 | Nathan Miles |
| M0.6: Platform–CPH integration scoping session with CPH engineer | 4/18/2026 | Nathan Miles + CPH contact |
| M0.7: CPFR Module scope document (MVP definition) agreed | 5/2/2026 | Nathan Miles + CPH contact + Erdem coaching |
| M0.8: Vendor scorecard mockup reviewed with ISMs and vendors | 5/16/2026 | Nathan Miles + Steven Palmer |

Phase gate: Cannot enter Phase 1 without (a) a confirmed CPH engineering contact, (b) an agreed MVP scope document, and (c) platform delivery confirmed. If the CPH contact is not identified by 4/18, this escalates to Dave Livesay for intervention.

## Phase 1: CPFR Module MVP Build (May–August 2026)

Funding model: Allocation transitioning to OP1 2027 submission.

Objective: Deliver a minimum viable CPFR presence in CPH that provides vendors with tangible value beyond email reports, while building the evidence base for OP1 2027.

MVP Definition (Scorecard-First Approach): Based on the 3/05 team alignment, the MVP leads with a vendor scorecard landing page—a visual executive summary with daily-refreshed metrics, tier-appropriate KPIs, and heat-map visualizations. This is paired with a basic report viewer (tier-based data access equivalent to current email content but on-demand) and self-service contact management (the structural fix for the data leakage vulnerability identified in the Kent → Kelcies incident).

| Milestone | Target Window | Owner |
| --- | --- | --- |
| M1.1: UX design for scorecard landing page and report viewer | May–June 2026 | Tamara’s team (pending Richard’s approval) or outsourced |
| M1.2: Vendor isolation alignment between CPH and SC-BIE semantic layer | May–June 2026 | CPH engineering + Stefan |
| M1.3: Scorecard landing page developed (front-end) | June–July 2026 | CPH engineering |
| M1.4: Basic tier-based report viewer integrated | July 2026 | CPH engineering + SC-BIE |
| M1.5: Self-service contact/distribution management in CPH | July–August 2026 | CPH engineering |
| M1.6: EDS security review completed | Parallel with M1.2–M1.5 | Replen Tech EDS partnership |
| M1.7: Internal beta with select ISMs and 10–20 Tier 2/3 vendors | August 2026 | Nathan Miles + Steven Palmer |
| M1.8: OP1 2027 submission drafted using MVP progress as evidence | August 2026 (aligned to OP1 cycle) | Nathan Miles + Phanindher |

Phase gate: Phase 1 completion requires (a) a functional CPFR module in CPH accessible by test vendors, (b) EDS security clearance, and (c) OP1 2027 submission in progress.

Critical dependency: CPH engineering capacity. If VC Phase 1 (Chargebacks) remains stalled and CPH capacity is not otherwise committed, the argument for directing that capacity to CPFR scoping and early build strengthens significantly. If VC un-stalls and consumes CPH capacity, Phase 1 timelines extend proportionally. This is the sequencing decision that leadership must resolve (see Section 4).

## Phase 2: General Availability & Scale (September 2026–January 2027)

Funding model: OP1 2027 funded (target). Fallback: continued allocation with extended timeline.

Objective: Roll out the CPFR module to all eligible vendors (Tiers 2 & 3), integrate email notification/fallback, and deliver the full self-service experience that eliminates Chewy as the manual scaling bottleneck.

| Milestone | Target Window | Owner |
| --- | --- | --- |
| M2.1: Phased vendor onboarding (waves of 200–500 vendors) | Sept–Nov 2026 | Nathan Miles + ISM team |
| M2.2: Email notification integration (alerts + fallback delivery) | Sept–Oct 2026 | CPH engineering |
| M2.3: Full report distribution management (vendor-controlled) | Oct–Nov 2026 | CPH engineering |
| M2.4: Performance validation at scale (3,000+ concurrent vendor tenants) | Nov–Dec 2026 | CPH engineering + SC-BIE |
| M2.5: Vendor adoption metrics baseline established | Dec 2026 | Nathan Miles + Amanda Greenslit (VX) |
| M2.6: GA achieved for Tiers 2 & 3 (2,229 vendors) | January 2027 | All |

Phase gate: GA declaration requires (a) all Tier 2 & 3 vendors onboarded or in onboarding queue, (b) email fallback operational, (c) vendor adoption tracking live, and (d) no critical performance degradation at scale.

## Phase 3: Tier 1 Enablement & Platform Maturation (Q1–Q2 2027)

Funding model: OP1 2027 funded.

Objective: Extend the platform to Tier 1 vendors (SKU/FC granularity), establish the API access path that major vendors have requested, and position the platform for advanced analytics/AI capabilities.

| Milestone | Target Window | Owner |
| --- | --- | --- |
| M3.1: SKU/FC-grain semantic table delivered by SC-BIE | Q1 2027 | Stefan / SC-BIE |
| M3.2: Tier 1 CPFR module extensions (granular views, catalog detail) | Q1–Q2 2027 | CPH engineering |
| M3.3: API access framework for premium vendors | Q2 2027 | CPH engineering + SC-BIE |
| M3.4: Analytics/AI foundation assessment (forecast accuracy, anomaly detection) | Q2 2027 | SC-BIE + CPFR team |

Persona note: Phase 3 is what makes the OP1 2027 submission a compelling multi-year story rather than a one-and-done request. Dave Livesay is positioned to push for SKU/FC grain priority with Stefan. The API access milestone directly addresses requests from Blue Buffalo, Mars, and Nestlé Purina, making vendor demand concrete for any portfolio evaluator.

## 3. Critical Path & Dependencies

The critical path runs through three constraints, in order of urgency:

| # | Constraint | Impact If Unresolved | Resolution Path |
| --- | --- | --- | --- |
| 1 | No confirmed CPH engineering contact | Entire roadmap blocked. Cannot scope, estimate, or begin integration work. | Escalation path: Nathan → Erdem (coaching offer activation) → Dave if no resolution by 4/18. |
| 2 | CPH capacity consumed by VC | Phase 1 timelines extend proportionally. If VC consumes all of Q2–Q3, CPFR module build slides to Q4 2026, potentially missing OP1 2027 evidence window. | Proposed: conditional parallel track—CPFR scoping proceeds in parallel with VC build. Zero-ramp-up when capacity pivots. (See Section 4.) |
| 3 | Design resource approval | UX design for scorecard and module delayed. Outsourcing fallback adds cost and coordination overhead. | Richard Neely’s approval pending. The unified vendor experience framing in PRFAQ and scope doc is designed to convert his concern into alignment. |

## 3.1 Dependency Map

The following dependency chain governs the sequencing of all milestones:

Platform (SC-BIE) ────────────▶  3/31 DELIVERED (network grain)

│

├── Vendor Isolation Alignment ─▶  CPH + SC-BIE coordination

│

├── CPH Contact Identified ─▶  Integration scoping session

│       │

│       └── MVP Scope Agreed ─▶  Phase 1 entry

│

├── Design Resources Approved ─▶  UX work begins

│

└── VC Phase 1 Status ─▶  CPH capacity pivot timing

## 4. Sequencing Decision: VC and CPFR in CPH

The original plan assumed VC (Chargebacks, then Violations) would prime the CPH engineering pipeline while SC-BIE built the CPFR data platform. Upon VC completion, CPH capacity would pivot to CPFR module work. This sequencing is now temporally inverted: the CPFR data platform will be ready on 3/31/2026, but VC Phase 1 has stalled in design/planning due to personnel churn.

This creates both a risk and an opportunity. If VC un-stalls, it legitimately consumes CPH capacity first, potentially pushing CPFR module work further out despite the platform being ready. However, CPH developers have not yet built muscle memory on the portal architecture through VC work, which was the original benefit of the sequencing.

## 4.1 Recommended Approach: Conditional Parallel Track

Rather than choosing between “wait for VC” and “compete with VC for capacity,” the roadmap recommends a lightweight parallel track for CPFR that does not draw on VC’s build capacity:

- CPFR scoping, design, and integration planning proceed in parallel with whatever VC work is active. This is primarily Nathan’s time plus intermittent CPH engineering consultation (not build capacity).

- When CPH capacity becomes available—whether because VC completes, VC remains stalled, or incremental capacity is allocated—CPFR module build begins with zero ramp-up time because scoping, design, and integration requirements are already complete.

- If VC unstalls and consumes all CPH capacity through Q3, the CPFR Module MVP build slides to Q4 but the scoping work done in parallel means the build window compresses rather than extending.

This approach threads the needle: it doesn’t threaten Richard Neely’s portfolio coherence (no competing demands on the same engineers), it costs near-zero marginal capacity, it maintains Nathan Nelson’s joint front (VC isn’t being deprioritized), and it converts idle time into readiness.

# 5. Resource Requirements

The following represents the estimated resource engagement needed across phases. These are engagement windows, not headcount requests—the OP1 2027 submission will translate these into specific provisioning asks.

| Role | Phase 0 | Phase 1 | Phase 2 | Notes |
| --- | --- | --- | --- | --- |
| Nathan Miles (CPFR PM/TPM) | Full engagement | Full engagement | Full engagement | Allocation—current role |
| CPH Engineer(s) | Consultation (intermittent) | 1–2 engineers (build) | 1–2 engineers (build + scale) | Critical gap—no contact identified |
| UX Designer | Not needed | Partial engagement | Minimal | Pending Richard’s approval (Tamara’s team) or outsource |
| SC-BIE (Stefan’s team) | Platform delivery | Integration support | Scale validation | Funded under existing SC-BIE charter |
| Steven Palmer (CPFR team) | Scorecard design input | ISM engagement, beta coordination | Vendor onboarding enhancements | Allocation—current role |
| Nathan Nelson (VC partner) | Co-presentation | Joint front for OP1 | VC/CPFR alignment | Allocation—current role |

Color key: Green = covered by current allocation. Yellow = intermittent/partial, achievable on allocation. Red = requires dedicated capacity (OP1 target).

# 6. Active Risk Register

This is a living document. Risks are reviewed weekly and updated as conditions change.

| ID | Risk | Prob. | Impact | Mitigation | Owner |
| --- | --- | --- | --- | --- | --- |
| R1 | No CPH engineering contact identified | High | Critical | Escalation ladder: Erdem coaching → Dave intervention. Hard deadline 4/18. | Nathan Miles |
| R2 | VC consumes all CPH capacity through Q3 | Medium | High | Conditional parallel track. CPFR scoping independent of VC build. | Nathan Miles / Nathan Nelson |
| R3 | Design resources not approved | Medium | Medium | Outsource fallback. Unified VX framing in all artifacts. | Nathan Miles / Phanindher |
| R4 | Vendor adoption below threshold | Low | High | Scorecard-first MVP; email fallback preserved; phased onboarding with ISM accountability. | Nathan Miles / Steven Palmer |
| R5 | Vendor isolation misalignment (CPH vs SC-BIE) | Medium | Medium | Early coordination in Phase 0. Configuration in line-of-sight before build. | CPH contact + Stefan |
| R6 | OP1 2027 submission not competitive | Medium | Critical | Allocation progress creates demonstrable evidence. Beta with real vendors by Aug 2026. | Nathan Miles / Phanindher |
| R7 | Data leakage incident before portal launch | Low | Critical | Manual process controls maintained. Portal self-service admin is the structural fix. | Nathan Miles / CPFR team |

# 7. OP1 2027 Positioning Strategy

Tom Burritt’s assessment—that this initiative probably won’t get real commitment until it reaches OP1—is an honest diagnosis. The roadmap is designed to convert that diagnosis from a death sentence into a staging plan.

## 7.1 The Arc: Allocation → Evidence → OP1

The goal between now and the OP1 2027 submission window (~August 2026) is to produce evidence that makes the OP1 case undeniable:

- Platform delivered on time (3/31). — Already happening.

- MVP scoped, designed, and (ideally) in early build or beta. — Proves tractability.

- Vendor demand documented with named accounts. — Already in hand.

- Competitive parity gap established (Amazon, Walmart). — Already documented.

- Data leakage risk articulated as structural vulnerability. — Already in PRFAQ.

The OP1 submission narrative writes itself if these five evidence points are in place: “We built the bridge. We proved the on-ramp works. Now fund the full lane.”

## 7.2 What OP1 2027 Funds Would Unlock

The distinction between allocation and OP1 should be crisp in the submission:

- On allocation: scoping, design, stakeholder alignment, scorecard mockups, limited beta (Phase 0 + early Phase 1). This is progress, but it’s fragile—it depends on individual contributors having bandwidth.

- With OP1 funding: dedicated CPH engineering for CPFR module build, general availability rollout to 2,229 vendors, Tier 1 SKU/FC granularity, API access for premium vendors, and the analytics foundation that extends platform value into AI/ML territory.

# 8. Governance & Cadence

- Weekly checkpoint: Run by Nathan Miles. Working-level status against milestones. Attendees: Nathan Miles, Steven Palmer (as needed), CPH engineering contact (TBD), Nathan Nelson (as needed). This is the coordination hub.

- Biweekly leadership update: Nathan Miles → Phanindher. One-page status, blockers, and escalation requests. Designed for Phanindher to relay upward with zero additional work.

- Monthly stakeholder review: Nathan Miles + Phanindher present to broader stakeholder group (Tom Burritt, Richard Neely as appropriate). Roadmap progress, risk register update, upcoming decision points.

- Escalation protocol: Phase gates that are blocked for >2 weeks trigger escalation through Phanindher to Dave. Each escalation arrives as a one-paragraph brief with a clear decision ask—not a problem statement.

# 9. Assumptions & Constraints

- CPH engineering capacity will become available for CPFR module work in Q2 or Q3 2026, either through VC completion, VC continued stall, or incremental allocation.

- The SC-BIE CPFR data platform will deliver as planned on 3/31/2026 at network grain with vendor isolation and daily refresh.

- Design resources (Tamara’s team or outsourced) will be available for Phase 1 UX work.

- The CPFR module must integrate into existing CPH architecture and maintain unified vendor experience (Richard Neely’s mandate).

- OP1 2027 planning cycle begins approximately June–August 2026; the roadmap is calibrated to produce demonstrable evidence by that window.

- Email-based CPFR distribution continues as a parallel channel during the transition period; the portal supplements rather than replaces email until adoption metrics confirm readiness for migration.

Document History: v0.1 (2026-03-11) — Initial draft for internal review.